## Sheet1
Task No. | When | Who will do it | Where is the URL? | What do you need to do?
1 | Before Mon 5PM | The control group members | www.lavalife.com | register onto and create a decent profile on Lavalife.com production.
2 | Tue 6:00AM | Jason Cui |  | do the database migration. It may take about 2 hours.
3 | Tue 8:30AM | Jeff Yang | http://webtest-app2 | prepare the pre-production environment (http://webtest-app2) and make it ready for test.
4 | Tue 10:00AM | The control group members | http://webtest-app2 | work on http://webtest-app2 and verify their profile been migrated
5 | Tue 11:00am | The control group members | http://webtest-app2 | register/create new profile with opposite gender;
6 | Tue 11:00am | The control group members | http://webtest-app2 | At this moment, everyone has two accounts (male and female). Then login in into these two accounts from different browsers (IE, Chrome, Firefox, Safari); at the same time and view profile/send smile/send backstage/block some guy and so on.
7 | Tue 2pm to 3pm | The control group members | http://webtest-app2 | all control group members are supposed to be online at http://webtest-app2 concurrently and do the load test.